## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
Login | Authentication | Simple | Iteration 1 | SE150785 | Đặng Minh Hoàng |  | 1
Register | Authentication | Simple | Iteration 1 | SE150785 | Đặng Minh Hoàng |  | 2
Password retrieval | Authentication | Simple | Iteration 1 | SE150785 | Đặng Minh Hoàng |  | 3
View Introduction and overview information | Overview information | Simple | Iteration 1 | SE150772 | Nguyễn Trung Minh Hiếu |  | 4
Search Information | Overview information | Simple | Iteration 1 | SE150772 | Nguyễn Trung Minh Hiếu |  | 5
View User information | User information | Simple | Iteration 1 | SE150849 | Hồ Đăng Khoa |  | 6
Update User information | User information | Simple | Iteration 1 | SE150849 | Hồ Đăng Khoa |  | 7
View News information | News Management | Simple | Iteration 1 | SE150796 | Nguyễn Lâm Hưng |  | 8
View News details | News Management | Simple | Iteration 1 | SE150796 | Nguyễn Lâm Hưng |  | 9
Search News | News Management | Simple | Iteration 1 | SE150796 | Nguyễn Lâm Hưng |  | 10
View dentist information | Dentist Information | Simple | Iteration 1 | SE150849 | Hồ Đăng Khoa |  | 11
View dentist details | Dentist information | Simple | Iteration 1 | SE150849 | Hồ Đăng Khoa |  | 12
View list service | Service Management | Simple | Iteration 1 | SE150772 | Nguyễn Trung Minh Hiếu |  | 13
Search service | Service Management | Simple | Iteration 1 | SE150772 | Nguyễn Trung Minh Hiếu |  | 14
Delete service | Service Management | Simple | Iteration 1 | SE150785 | Đặng Minh Hoàng |  | 15
Add new service | Service Management | Simple | Iteration 1 | SE150785 | Đặng Minh Hoàng |  | 16
Edit the service | Service Management | Simple | Iteration 1 | SE150796 | Nguyễn Lâm Hưng |  | 17
View service detail | Service Management | Simple | Iteration 2 | SE150796 | Nguyễn Lâm Hưng |  | 18
View booking schedule | Booking Management | Medium | Iteration 2 | SE150849 | Hồ Đăng Khoa |  | 19
Add new booking | Booking Management | Medium | Iteration 2 | SE150849 | Hồ Đăng Khoa |  | 20
Add service to the booking | Booking Management | Medium | Iteration 2 | SE150772 | Nguyễn Trung Minh Hiếu |  | 21
Edit booking info | Booking Management | Simple | Iteration 2 | SE150772 | Nguyễn Trung Minh Hiếu |  | 22
View history booking info | Booking Management | Simple | Iteration 2 | SE150772 | Nguyễn Trung Minh Hiếu |  | 23
Search history booking | Booking Management | Simple | Iteration 2 | SE150772 | Nguyễn Trung Minh Hiếu |  | 24
View notification | Announcement | Simple | Iteration 2 | SE150785 | Đặng Minh Hoàng |  | 25
Delete nottification | Announcement | Simple | Iteration 2 | SE150785 | Đặng Minh Hoàng |  | 26
Check booking status | Booking Management | Simple | Iteration 2 | SE150785 | Đặng Minh Hoàng |  | 27
Confirm booking | Booking Management | Simple | Iteration 2 | SE150785 | Đặng Minh Hoàng |  | 28
Export booking info | Booking Management | Simple | Iteration 2 | SE150849 | Hồ Đăng Khoa |  | 29
Chat with staff | Customer service | Complex | Iteration 2 | SE150849 | Hồ Đăng Khoa |  | 30
Reply customers | Customer service | Complex | Iteration 2 | SE150849 | Hồ Đăng Khoa |  | 31
Block account | User Management | Simple | Iteration 2 | SE150796 | Nguyễn Lâm Hưng |  | 32
List of statistics | User Management | Medium | Iteration 2 | SE150796 | Nguyễn Lâm Hưng |  | 33
List of user register | User Management | Medium | Iteration 3 | SE150796 | Nguyễn Lâm Hưng |  | 34
Export Excel file | User Management | Medium | Iteration 3 | SE150796 | Nguyễn Lâm Hưng |  | 35
Add Clinic | Dentist management | Simple | Iteration 3 | SE150796 | Nguyễn Lâm Hưng |  | 36
Update Clinic | Dentist management | Simple | Iteration 3 | SE150796 | Nguyễn Lâm Hưng |  | 37
DeleteClinic | Dentist management | Simple | Iteration 3 | SE150796 | Nguyễn Lâm Hưng |  | 38
Search Clinic | Dentist management | Simple | Iteration 3 | SE150772 | Nguyễn Trung Minh Hiếu |  | 39
View Clinic | Dentist management | Simple | Iteration 3 | SE150772 | Nguyễn Trung Minh Hiếu |  | 40
Write feedback | Customer service | Simple | Iteration 3 | SE150849 | Hồ Đăng Khoa |  | 41
Update feedback | Customer service | Simple | Iteration 3 | SE150849 | Hồ Đăng Khoa |  | 42
Delete feedback | Customer service | Simple | Iteration 3 | SE150849 | Hồ Đăng Khoa |  | 43
View Feedback | User Management | Simple | Iteration 3 | SE150772 | Hồ Đăng Khoa |  | 44
Search Feedback | User Management | Simple | Iteration 3 | SE150772 | Nguyễn Trung Minh Hiếu |  | 45