## Week_1
PROJECT REPORT
Group | KHL
Week | 09/05/2022 - 15/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | List out requirement | In Progress | List out the requirements that the user wants.
2 | Description of functions | In Progress | This function is capable of doing what.
3 | User classification | Completed | Categorize who will use the software.
4 | Draw booking system context diagram | Completed | The interaction of each type of user with the system.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | List out the requirements that the user wants. | HieuNMT | Learn from similar websites.
2 | Analyze requirement feasibility | HungNL | Understand each member's ability to decide.
3 | User classification | HoangDM
4 | Description of functions | KhoaHD
5 | Draw booking system context diagram | HungNL
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | There are still some unclear requirements. | Pending | Read more document on Internet.
2 | Do not agree with each other on the functions | In Progress | Through the following meetings to clarify the issue.
3 | Context diagram still missing | In Progress | Draw more things that are missing.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Draw screen flow | 18/05 | Online reference.
2 | Unified the functions | 19/05 | Discuss and refer to the app on the market.
3 | App interface sketch | 20/05 | Discuss and agree on members' opinions.
V. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Website skeleton | HieuNMT | Need to match the given theme, in terms of UI the color should match the theme.
HoangDM
2 | Screen flow | KhoaHD | Add to the idea suggested by mentors.
3 | Payment System | HungNL | Learn about online payment methods to apply to the system.

## Week_2
PROJECT REPORT
Group | KHL
Week | 16/05/2022 - 22/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Fix the problem in SRS 1.2 Introduction. | Completed | Complement to complete.
2 | Search Web Skeleton | Completed | Need to match the given theme.
3 | Update working schedule | In Progress | Arrange a suitable schedule to work effectively.
4 | Draw wireframe | In Progress | Outline buttons on a web page.
5 | Identify entity | In Progress | Determine rigor as well as complete entities in the database.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Draw screen flow | HieuNMT | Add missing screen
2 | Unified the functions | HungNL | Learn from similar websites.
3 | Draw wireframe on web online | HoangDM | Based on the guidance of the mentor.
4 | Create database | KhoaHD | Ask your mentor for objective comments.
5 | Define User Authorization in SRS | KhoaHD | Complete the document at Part 1.2.
6 | Write backlog | HungNL | Appropriate division of work so that everyone can promote their strengths.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Problem in define entity in database | In Progress | Define wrong entity
2 | Designing the wireframe | In Progress | Design of buttons and internal data fields used
3 | Determination of the functionality of the web | In Progress | Based on online websites to get the most correct functions.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Start coding as planned | 2022-05-27 | Each member as least 3 functions
2 | Comple the SRS Part 1 | 2022-05-27 | Editing based on suggestions from mentors.
3 | Doing in the SRS 2.1 Feature | 2022-05-27
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Add 1 more user : Guest | HungNL | Guest will able to book the order but not need to log in.
2 | Payment system | HungNL | Learn about online payment methods to apply to the system.

## Week_3
PROJECT REPORT
Group | KHL
Week | 23/05/2022 - 29/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Completing wireframe drawing | In Progress | Draw the entire wireframe for the screens and describe the functions
2 | Complete product backlog | In Progress | This function is capable of doing what.
3 | Answer questions on edunext | Completed | Categorize who will use the software.
4 | Complete SRS part 2 | In Progress | Add detail
5 | Find and Add more Functional Requirements | In Progress | Discussion, analysis to add functions
6 | Edit and complete the database | In Progress | edit, add or remove objects
7 | Complet the SRS Part 1 | Completed | Add the missing information
8 | Completing erd diagram | Completed | Complete the ERD based on the suggestion
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Draw wireframe | HieuNMT | Draw the entire wireframe for the screens and describe the functions
HoangDM
2 | Division of work in product backlog | HungNL | Appropriate division of work so that everyone can promote their strengths.
3 | Try to comple Database | KhoaHD
4 | Create our webskeleton | KhoaHD
5 | Draw ERD | HungNL | Try to comple based what mentor suggested
6 | Fix and update the SRS Part 1 | HungNL | Add more function and the new screen flow
7 | Add wireframe to SRS Part 2 | HieuNMT | Add wirreframe and the desription of each wireframe.
HoangDM
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Context diagram still missing | In Progress | Read more document on Internet.
2 | Missing function | In Progress | Through the following meetings to clarify the issue.
3 | Unified web interface | Completed
4 | Pproblem with ERD | In Progress | Draw more things that are missing.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Start code based on product backlog | 2022-06-03
2 | Complete database and ERD | 2022-06-03 | Editing based on suggestions from mentors.
3 | Doing the Design document | 2022-06-03
V. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Add 1 more user : Guest | HungNL | Guest will able to book the order but not need to log in.
2 | Payment system | HungNL | Learn about online payment methods to apply to the system.

## Week_4
PROJECT REPORT
Group | KHL
Week | 30/05/2022 - 05/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Complete context diagram. | Completed | Add more function to the diagram
2 | Meeting on 30/04 about fixing database | Completed | We give opinions to be able to agree on the database.
3 | Fixing SRS Part 2 and complete it | In Progress | Add wireframe to complete the SRS
4 | Add ERD to the Design Document. | Completed | Add information to the design document
5 | Add table detail to Design Document | In Progress | Add table in database to complete 1 part in the design documents
6 | Meeting on 01/05 about managing code | Completed | Manage Git and github about pull and pushh code
7 | Code Home Page | Completed | Start code the homepage with the wireframe given.
8 | Code About us page | Completed | Coding about us.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Complete database | All member | From everyone's opinion and unify the database.
2 | Fixing SRS Part 2 | HungNL | Complete the missing parts of the team.
3 | Add ERD to the Design Document. | HungNL | Write details of the ERD table.
4 | Add table detail to Design Document. | HieuNMT | Specify the values ​​of each table as well as the variables in the table
5 | Working with git to manage code | HoangDM
6 | Code Home Page | KhoaHD
7 | Code About us page | KhoaHD
8 | Draw content diagram | HieuNMT | Added a few things from last week.
9 | Code News Page | HoangDM
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Draw Sequence Diagram | In Progress | Ask mentor to have experience
2 | Draw class Diagram | In Progress | Consult on the internet to have the necessary knowledge to do
3 | Draw code packages | In Progress | Need to draw correctly
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Start doing code based on backlog of interation 2 | 2022-06-11
2 | Complete 9 function | 2022-06-06
3 | Try to complete Design Document | 2022-06-10 | Editing based on suggestions from mentors.
V. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Add 1 more user : Guest | HungNL | Guest will able to book the order but not need to log in.

## Week_5
PROJECT REPORT
Group | KHL
Week | 06/06/2022 - 12/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | List of the 5 core flow | In Progress | To show the core to the mentors
2 | Do Edunext | In Progress | complete the question on the system
3 | Try to do the Part 1 of Design Document | Completed | Editing based on suggestions from mentors.
4 | Code News Part | Completed | Complete the function about the News Part
5 | Code Login Part | Completed | Complete the function about the Login Part.
6 | Code Dentist Part | Completed | Complete the function about the Dentist information Part.
7 | Code interface of the Booking | In Progress | Complete the interface about the booking Part.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Complete Edunext of this week | All member
2 | Draw 5 core flow | HungNL
3 | Do Part 1 of Design Document | HieuNMT | Try to draw class Diagram
4 | Code News Part | HoangDM
5 | Code Login Part | KhoaHD | including front-end and backend
6 | Code Dentist Part | HieuNMT | including front-end and backend
7 | Code Admin Page | KhoaHD | including front-end and backend
8 | Code interface of the Booking | HungNL
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Miss understand the core flow | Completed | Get some help form the mentor
2 | The progress of coding function is too slow | In Progress | redistribute to speed up the progress
3 | Draw Sequence Diagram | In Progress | Ask mentor to have experience
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete Part 2 Design Documents | 2022-06-24
2 | Try to complete Iteration 2 and 1 | 2022-06-22
V. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Payment system | HungNL | Learn about online payment methods to apply to the system.

## Week_6
PROJECT REPORT
Group | KHL
Week | 13/06/2022 - 19/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | List of the 5 core flow | Completed | To show the core to the mentors
2 | Do Edunext | In Progress | Answer all the question by slot.
3 | Meeting on 15/6 about the coreflow | Completed | To unify the idea about the coreflow.
4 | Code admin feature | In Progress | Complete the back-end part.
5 | Code interface of the Booking | In Progress | Complete the interface about the booking Part.
6 | Check again SRS | Completed | Complete all the missing part.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Complete Edunext of this week. | All member
2 | Draw 5 core flow. | All member
3 | Doing backend of booking part. | HungNL | Complete the backend.
4 | Doing export data in admin feature. | KhoaHD | Fixed some features suggested by the mentor.
5 | Fixing bug at edit profile part | HieuNMT | Fixed some features suggested by the mentor.
6 | Fixing bug at Dentist part | HoangDM | Fixed some features suggested by the mentor.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Draw Sequence Diagram | In Progress | Consult on the internet to have the necessary knowledge to do.
2 | Draw Class Diagram | In Progress | Ask a mentor for clarification.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Start doing the chat box part | 2022-06-24
2 | Start doing the feeback part | 2022-06-24
3 | Start doing employee feature | 2022-06-24
V. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## Week_7
PROJECT REPORT
Group | KHL
Week | 20/06/2022 - 25/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Do Admin feature add hospital | In Progress
2 | Do Edunext | In Progress | Answer all the question by slot.
3 | Meeting on 20/6 about the bussinessrule | Completed | To unify the idea about the coreflow.
4 | Draw class diagram | In Progress | Complete the back-end part.
5 | Draw sequence diagram | In Progress | Complete the interface about the booking Part.
6 | Fix bug at booking service | In Progress
7 | Doing Service detail | Completed | Complete all the missing part.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Complete Edunext of this week. | All member
2 | Doing backend of booking part. | HungNL
3 | Draw class diagram
4 | Draw sequence diagram
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Draw Sequence Diagram | In Progress | Consult on the internet to have the necessary knowledge to do.
2 | Draw Class Diagram | In Progress | Ask a mentor for clarification.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes